## Sheet1
Current Submission for Team ___Organization of Programming Students, OPS
Tag | Date | Submission | Description of Changes
ActDue01 | 2015-09-04 | Team Project Ideas | Team formation, proposed projects, summary of work to be done.
ActDue02 | 2015-09-25 | Software Requirements | Software Requirements Specification - Use cases division
ActDue03 | 2015-10-02 | Finshed SRS and posted | Finished SRS and posted to the BlackBoard
ActDue04 | 2015-10-09 | Software Selection | Selected Java and started creating the project classes and screens
ActDue05 | 2015-10-16 | First Sprint Started | Programminng Frames : Eric(SetupSummary), Ruth (AnswerEntry), Brian (QuestionSelect), Laercio (GameStatus) and Alesander (WinnerSelect)
ActDue06 | 2015-10-23 | Created All Screen Frames | The first screen frames were created but not fully operational yet.
ActDue07 | 2015-10-30 | Trivia started working from start to finish | The team had all integration code done so it could start logic working.
ActDue08 | 2015-11-06 | Changed the screens to have the same A-frame | All screens were re-code to use the same Jframe and start using Jpane as homework.Some other improvements as resizing the Jpanel, centering in the screen. Finish first sprint.
ActDue09 | 2015-11-13 | Start Second Sprint